## Cost estimate_total (hidden)
Install borders |  |  | Unit Cost
Labour hours | h | 16 | Concrete | MMK/m³ | 1000 | red values | Fill in
length | m | 100 | Rebars | MMK/m | 1000 | Grey values | Estimations/formula. Do not change
volume of concrete needed | m³ | 1 | Steel bar | MMK/m | 2000 | Bolt Black values | results. Do not change
Total cost to install borders | MMK | 161000 | Wooden bar | MMK/m | 1000
Install covers |  |  | Chiken wire | MMK/m² | 1000
Labour hours | h | 20 | Dredging tools | MMK/d | 1000
length | m | 100 | Bricks | MMK/m³ | 1000
Width | m | 0.5 | Mortar | MMK/m³ | 1000
Thickness | m | 0.1 | Corrugated iron | MMK/m² | 1000
volume of concrete needed | m³ | 5 | Wood/bamboo | MMK/m² | 1000
estimated length of ribars needed | m | 40.3333 | Gibon Wall | MMK/m³ | 1000
Total cost to install covers | MMK | 245333.3333 | Labour hours | MMK/h | 10000
Install grids
Labour hours | h | 16
Bar material | - | steel
bars (wood/steel) | m | 30
Chicken wire | m² | 20
Total cost to install grids | MMK | 240000
Dredging sediment
Labour hours | h | 160
Dredging tools (crane, truck, …) | MMK | 20000
Total cost to dredge sediment | MMK | 1620000
Removing solid waste
Labour hours | h | 160
Dredging tools (crane, truck, …) | MMK | 20000
Total cost to remove solid waste | MMK | 1620000
removing vegetation
Labour hours | h | 160
Dredging tools (crane, truck, …) | MMK | 20000
Total cost to remove vegetation | MMK | 1620000
Reinforce Channels
Length | m | 100
depth | m | 1
Concrete
Estimated amount of concrete | m³ | 6
Labour hours | h | 100
Total Concrete reinforecment | MMK | 1006000
Bricks
Labour hours | h | 100
Volume of wall | m³ | 9
Estimated # bricks | # | 4500
Mortar | m³ | 2.0745
Total brick wall reinforecment | MMK | 5502074.5
Corrugated sheets
Labour hours | h | 100
Estimated surface of sheets | m² | 100
Estimated length of wooden bars | m | 66.6667
Total brick wall reinforecment | MMK | 1166666.667
Wooden planks
Labour hours | h | 100
Estimated lenght of wooden planks | m | 500
Estimated length of wooden bars | m | 66.6667
Total brick wall reinforecment | MMK | 1566666.667
Gibon Wall
Labour hours | h | 100
Estimated volume of Gibon wall | m³ | 20
Total brick wall reinforecment | MMK | 1020000

## work_per_section
[2] |  |  |  | Location 1: outlet 1 | Location 2: stretch between outlet 1 and Min Nandar road |  | Location 3: Culvert near Fortune Plaza | Location 4: culvert near 'entrance' fortune plaza | Location 5: stretch between Fortune Plaza & Ward 5 |  | Location 6: Culvert Myin Taw Thar Road/ Ward | Location 7: Drain along Myin Taw Thar road |  | Location 10: Outlet 4 | Location 11: creek towards river |  | Location 12: Culvert near outlet 4 | Location 13: Ward 5 - > outlet |  | Location 14: Ward 5 Shukinhtar road
[5 empty] | 120 | m |  |  | 600 | m |  | 500 | m |  | 200 | m |  | 470 | m | 420 | m
Interventions: |  |  |  |  | 393.72 | feet |  |  | 1968.6 | feet |  | 1640.5 | feet |  | 656.2 | feet |  | 1542.07 | feet | 1378.02 | feet
1 | Maintain/ fix outlets |  |  | Maintain/fix outlets |  |  | Reinstall flood gates? | [6 empty] | Maintain/fix outlets
| fix hinges | # |  | 1
2 | Install borders |  |  | Install border |  |  |  | Install border | Install borders |  |  |  |  | Install border |  |  | Install borders
| length | m
3 | Install covers | [16 empty] | Install covers
| length | m
4 | Install grids |  | see special tab | Install grid |  |  |  | Install grids |  |  | Install grids |  |  | Install grid |  |  | Install grid at underground passage |  |  | Install grids at under ground passages
| # | #
5 | Dredging sediment |  |  | Dredging sediment |  |  | Dredging sediment |  | Dredging sediment |  | Dredging sediment | Dredging sediment |  | Dredging sediment | Dredging sediment |  | Dredging sediment | Dredging sediment
| length | m | [6 empty] | 900m...
6 | Removing solid waste |  |  | Remove solid waste |  |  | Remove solid waste | Remove solid waste | Remove solid waste |  | Remove solid waste | Remove solid waste |  | Remove solid waste | Remove solid waste |  | Remove solid waste | Remove solid waste |  | Remove solid waste
| length | m
7 | removing vegetation |  |  | Remove vegetation | Remove vegetation |  | Remove vegetation | Remove vegetation | Remove vegetation |  | Remove vegetation | Remove vegetation |  | Remove vegetation | Remove vegetation |  | Remove vegetation | Remove vegetation |  | Remove vegetation : fallen tree in water(?)
| length | m
8 | Reinforce Channels |  | see special tab |  |  |  |  | Reinforce channels: To be discussed locally Not main priority - but good to do area close to culvert | Reinforce channels: To be discussed locally Not main priority to do whole stretch - focus on locations where drain is smallest and/or erosion takes place |  | Reinforce channels - improve current structure, also other side - connect to drain (location 6) | Reinforce channels - keep area green and attractive (near park) |  |  | Reinforce channels: To be discussed locally Finalize reinforcing channel (partly done already) |  |  | Improve drain along road - ensure enough capacity, build proper tunnels and culverts were needed |  | Improve drain along road - ensure enough capacity, build proper tunnels and culverts were needed. Combine with buffer location; overview possible.
| Concrete | [6 empty] | 2. Concrete and/or brick - only sides (no concrete bottom) | 2. Concrete and/or brick - only sides (no concrete bottom) |  | 2. Concrete and/or brick - only sides (no concrete bottom) | 2. Concrete and/or brick - only sides (no concrete bottom)
| length | m
| depth | m
| Bricks | [16 empty] | Bricks with U/V shape (see sketch @nr. 9 next tab) |  | Bricks with U/V shape (see sketch @nr. 9 next tab)
| length | m
| depth | m
Corrugated sheets
| length | m
| depth | m
| Wooden planks | [9 empty] | 1. Corrugated sheets or wooden planks - more infiltration, cheaper | 1. Wooden planks - improve/ complete current structure (or already done in concrete?)
| length | m
| depth | m
| Gibon Wall | [6 empty] | 1. Gibon Wall (as there is space available, increases infiltration) | 1. Gibon Wall (keeps area open, attractive, less concrete)
| length | m
| depth | m
| Rip Rap | [13 empty] | Rip Rap (as done now)- but also good to keep drain natural (infiltration, biodiversity, adaptive)
| length | m
| depth | m
9 | Tunnel | [16 empty] | Make proper tunnel underneath roads/drive ways. A concrete pipe or a covered channel. If possible, foresee man holes in order to clean |  | Make proper tunnel underneath roads/drive ways. A concrete pipe or a covered channel. If possible, foresee man holes in order to clean
Concrete pipe
covered drain
10 | Verify Slope: outlet= lowest point, slope of min 0.3% preferable 0.5% | [7 empty] | Verify slope |  |  | Verify slope | [5 empty] | Verify slope |  | Verify slope, especially around 'swamp' area.

## Reinforcing channels
Channel reinforcement
1. Wooden planks
instructions: https://gadero.be/afboording-bouwen/
|  |  | + | -
|  |  | Easy | Requires maintenance
|  |  | Withouth plastic sheet: allows infiltration | For deep channels: need reinforcement bars => Takes in more space then shown (1m from border)
Low Capex
2. Gibon wall
Instructions: http://gardendrum.com/2012/04/21/how-to-build-a-gabion-wall/
|  |  | + | -
|  |  | Can be "Cheap" if brick/rubble is available from construction | Takes in a lot of space: only intersting for bigger channel
Allows infiltration
Low maintenance
3. Concrete wall
| Instructions: known |  | + | -
|  |  | Compact | No infiltration
|  |  | Low maintenance | High capex
Low friction
4. Bricks
| Instruction: known |  | + | -
|  |  | Easy | No infiltration possible
|  |  | minimal space needed | High Capex
fast installation
Low maintenance
Low friction
5. Rip rap
| Instruction: Known |  | + | -
|  |  | Good to make V-shape channels: best velocity profile | needs a lot of space
|  |  | Can be "Cheap" if Rocks/Rubble is available | High Capex
6. Bamboo mat
| Instructions: see sketch |  | + | -
|  |  | Local material | Requires maintenance
|  |  | Infiltration possible | High friction due to vegitation
Good to keep small "natural" creeks open
Fast to instal
Low Capex
8. Concreet V-channel
| Instructions | See drawing
|  |  |  | + | -
|  |  |  | Can be cheaper then concrete U-channels | More expensive then non-concrete solution
for smaller channels, precast can be done
Fasted water velocity: removal of waste
Less chance on still standing water
It could be cheaper than cast-in situ. Precast drain length can be smaller depend on size of drain looking at its weight to handle manually by men. The bed slope of drain should not be smaller than 1:250. 1:200 would be the best. Rectangular sump with the width of min 1.5xdrian width is recommended to provide every 60m run or 90 degree turn. 20x50 or bigger GI metal mesh screen shall be provided in the outlet of sump to collect rubbish.
9. Brick U/V hybride
+
Combines the merits of U and V chanels
10. Corrugated sheets
| Instruction: known |  | + | -
| Make sure water can enter the creek (not like picture) |  | Easy to install/fast | Maintenance required
|  |  | Low Capex | Only good for shallow creeks
Does not look nice

## Waste grid
Waste grid
| Instructions | Use a construction of PVC pipes to improvise a grid
You can use a mesh as well if the channel is too wide.
Don't make mesh too small. For ex. 20x20cm
Clean grid at least 1/day. Otherwise channel will block.
| Where | Before every inlet of an underground passage
Before entering main collectors